## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 42.5 | 0 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-02-15 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Brainstorm topic | AB |  | 1 | 0 | 1 |  | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Assigned
6 | 1 | Research similar games | AB |  | 2 | 0 | 1.5 |  | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 1 | Write Research and Analysis | AB |  | 2 | 0 | 2.5 |  | 2 | 2 | 2 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Ball | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Walls | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Goal | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 1 | Tile selection area | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 1 | Go! button | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Stop! button | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Basic tiles | AB |  | 4 | 0 | 3.5 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2 | Velocity meter | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2 | Click-walls | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
17 | 4 | Game start screen | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
18 | 3 | Level select screen | AB |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
19 | 2 | Basic enemies | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2 | Doors/keys | AB |  | 0.5 | 0 | 1.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
21 | 2 | Rotational tiles | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
22 | 3 | Pushable blocks | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
23 | 3 | Jump tiles (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | Circular path enemies | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
25 | 3 | Enemy buttons/traps (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 2 | Holes | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 4 | Teleport tiles | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
28 | 4 | Teleport click (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | Level 1 | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | Level 2 | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 2 | Level 3 | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 2 | Level 4 | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
33 | 2 | Level 5 | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
34 | 2 | Level 6 | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
35 | 2 | Level 7 | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
36 | 3 | Level 8 | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
37 | 3 | Level 9 | AB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
38 | 3 | Level 10 (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Music | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0
40 | 2 | Sounds | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
41 | 2 | Fixed tiles | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
42 | 4 | Level 11 (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4 | Level 12 (Cut) | AB |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 4 | Level 2.5 | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
45 | 4 | Level 3.5 | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
46 | 4 | Level 4.5 | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
47 | 4 | Level 5.5 | AB |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
48 | 4 | Level 6.5 | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
49 | 4 | Level 7.5 | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
50 | 4 | Level 8.5 | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
51 | 4 | Message window design | AB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
52 | 4 | Message window in levels | AB |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
53 | 5 | Final testing | AB |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
54 | 5 | Write Justification Document | AB |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
55 | 5 | Victory screen | AB |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Arrow facing wall bounces ball in opposite direction | AB |  | 0.5 | 0 | 0.25 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | Fixed
108 |  | Ball may not have correct starting direction...? | AB |  | 0.5 | 0 | 0.25 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Can't Repro
109 |  | Enemies bounce on lifted tiles | AB |  | 0.5 | 0 | 0.25 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 |  | Die + touch goal = win? | AB |  | 0.5 | 0 | 0.25 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Can't Repro
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 42.5 | 42.5 | 39.4643 | 36.4286 | 33.3929 | 30.3571 | 27.3214 | 24.2857 | 21.25 | 18.2143 | 15.1786 | 12.1429 | 9.1071 | 6.0714 | 3.0357 | 0
212
213 |  | Sum | [6 empty] | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 14.5 | 14 | 12.5 | 12.5 | 11 | 8 | 4.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 7.75 | 7.75 | 6.25 | 3.75 | 0.75 | 0.75 | 0.75 | 0 | 0
217 |  |  | 3 | [5 empty] | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 2 | 2 | 0 | 0
218 |  |  | 4 | [5 empty] | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9 | 4 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Austin Brehob | AB |  |  |  |  | AB | 44.5 | 44 | 42.5 | 42.5 | 41 | 38 | 34.75 | 28.25 | 28.25 | 26.75 | 24.25 | 20.75 | 15.25 | 10.25 | 3.5 | 0
223 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5 | 42.5
236

## Daily Scrum
Producer | 2017-02-15 |  | Team Members
Approved | Dates |  | Austin Brehob | All
| 2017-02-01 | Wed | Done: Thought about what type of game to implement Next: Think about general game details Help: --
| 2017-02-02 | Thu | Done: Researched similar games Next: Finish researching similar games Help: --
| 2017-02-03 | Fri | Done: Nothing today Next: Finish researching similar games, write Research and Analysis Help: --
| 2017-02-04 | Sat | Done: Finished researching similar games, started to write Research and Analysis Next: Finish writing Research and Analysis Help: --
| 2017-02-05 | Sun | Done: Finished Research and Analysis, created burndown chart, created basic elements of game like ball, walls, and goal Next: Build level boundary, tile selection area, "Go!" and "Stop!" buttons Help: --
| 2017-02-06 | Mon | Done: Created level boundary, tile selection area, "Go!" and "Stop!" buttons, and bouncing arrow for informing player of ball's initial direction Next: Do as many of the following items as possible: Create place-able tiles, velocity meter, basic enemies; add levels 1-3, music, and sounds Help: --
| 2017-02-07 | Tue | Done: Created basic tiles, velocity meter/ability to change velocity, levels 1 and 2, and some music/sounds Next: Get some sleep! Help: --
| 2017-02-08 | Wed | Done: Slept a lot Next: Create enemies, add click-walls and holes, create levels 3 and 4 Help: --
| 2017-02-09 | Thu | Done: Created enemies, holes, and level 3 Next: Program fixed tiles and rotation tiles, and design levels 4 and 5 Help: --
| 2017-02-10 | Fri | Done: Created fixed and rotation tiles, and generated levels 4 and 5 Next: Implement click-walls and doors/keys, and design levels 6 and 7 Help: --
| 2017-02-11 | Sat | Done: Put click-walls and doors/keys into the game, and created levels 6 and 7 Next: Implement pushable blocks, circular-path enemies, enemy buttons/traps, teleport tiles, and teleport click, and create levels 8 and 9 Help: --
| 2017-02-12 | Sun | Done: Created pushable blocks, circular-path enemies, and teleport tiles, designed levels 8 and 9, and cut some planned tasks Next: Design level 10, and implement game start screen and level select screen Help: --
| 2017-02-13 | Mon | Done: Talked with Professor Bloch, who said I should create more levels introducing the player to new mechanics; implemented levels 2.5-8.5 as a result Next: Implement game start screen and level select screen, make messages to help introduce player to new mechanics, make game "juicier", change music and add more sounds, test a LOT, and write Justification Document Help: --
| 2017-02-14 | Tue | Done: Created game start and level select screens, designed/wrote messages to help introduce player to new mechanics, decided to not change music, added more sounds, did some testing Next: Make game "juicier", test more, and write Justification Document Help: --
| 2017-02-15 | Wed | Done: Added a bit of "juice", wrote Justification Document, and performed final test Next: -- Help: --
| 2017-02-16 | Thu
| 2017-02-17 | Fri
| 2017-02-18 | Sat
| 2017-02-19 | Sun
| 2017-02-20 | Mon
| 2017-02-21 | Tue
| 2017-02-22 | Wed